## CONCEPT
NO CONNECTION |  |  |  |  | LAPTOP BUKAN IP67 |  |  | laptop rusak |  |  | DAMPAK
trainer | menyenggol gelas berisi air / menumpahkan air | [9 empty] | DATA MENGAJAR RUSAK |  |  | LOSS = 1 M
[8 empty] | X NO CONTROL/ action needed >> |  | INHERENT RISK | RISK APETITE/CAPACITY (LOSS SCENARIO)
Priority
| Intentional / UNINTENTIONAL | [16 empty] | RPN
|  | ERROR |  |  |  | IT ASSETS |  | CONTROL PREVENTIVE) | RISK (uncertainty)
THREAT |  |  | X | VULNERABILITIES
ACTOR | EVENT | FRAUD |  |  | TANGIBLE |  | INTENGIBLE
[5 empty] | SERVER | SERVER | i.p
|  |  |  | 1q | JARINGAN | JARINGAN | SKILL & KNOWLEGDE |  | probability/ possibility |  | IMPACT/ MAGNITUDE |  | EXPOSURE/SEVERITY |  | DETECTION | EFFECT / CONSEQUENCIES |  |  | DESIGN CONTROL
CONTROL DETTERENT | CONTROL DETECTIIVE |  |  |  | LAPTOP | LAPTOP | BUDGET | [8 empty] | +$$$
[5 empty] | PEOPLE | LICENSE | SOURCE CODE | [8 empty] | -$$$
PROCESS / CONTRACT
UNPROPER CONTROL
|  |  |  | 10 LAPTOP |  |  |  |  | Necessary action>>>>>> | RESIDUAL RISK | CONTROL CORRECTIVE |  |  | treatment / response
|  |  |  | RISK TOLLERANCE ¦ RISK APETITE | [9 empty] | decision
|  |  |  | ACCEPTANCE (CAPACITY) | MITIGATION
|  |  |  | 2 LAPTOP | 8 LAPTOP
|  |  |  | MONITOR/ DETECTIVE | PREVENTIVE
INTERNAL AUDITOR
|  |  |  | 20 JUTA (ACCEPTANCE) | 80 JUTA (MITIGASI)
[5 empty] | RISK TRANSFER (50 JUTA) | RISK MITIGATION ( 20 JUTA) | RISK AVOIDANCE (-1) (10 JUTA) |  | ASSET | possibility |  |  | SEVERITY |  | DETECTION | ` | RPN
[5 empty] | sewa laptop (5) 500 rb KE CV ADIKARYA | 2 laptop di mitigasi OLEH TIM IT | 1 LAPTOP DITARIK |  | LAPTOP RUSAK | 3 |  |  | 3 |  | 3 |  | 27
[9 empty] | LAPTOP HILANG | 3 |  |  | 3 |  | 1 |  | 9
EVENT MANAGEMENT
liikeloohod
SCOPE
| PRODUK | UII GATEWAY | MODUL : PERKULIAHAN, PENJADWALAN , UJIAN , TAGIHAN
| UNIT BUSINESS | MARKETING
AKADEMIK
KEUANGAN
NETWORK
| SUBJECT AREA | AKADEMIK
|  | MAHASISWA | MOD : PERKULIAHAN
DOSEN
NILAI
REGISTRASI
| CONTEXT | PENERIMAAN MAHASISWA BARU 2025-2026
[7 empty] | VALUASI | EXPOSURE | SLE | ARO | ALE
[5 empty] | 1 | CBA | 4800000 | 0.25 | 1200000 | 25000 | 30000000000
| ASESSMENT (IDENTIFICATION) |  |  |  | 2 | CBA | 4800000 | 0.25 | 1200000 | 25000 | 34000000000
ASSET
SERVER
NETWORK
DATABASE
PEOPLE (MAHASISWA, DOSEN, STAFF AKADEMIK, DBA)
LOSS SCENARIO
| MODUL | ASSET | THREAT |  | RISK | IMPACT | LOSS SCENARIO
|  |  | ACTOR | EVENT
| MOD PERKULIAHAN (MAHASISWA) | PEOPLE | DBA | MISSCONFIGURATION | DATA/ FILE HILANG | INFORMASI TIDAK AVAILABLE, UPLOAD ULANG DOKUMEN | 30000000000
|  | PEOPLE | DBA | KELALAIAN | DATA/ FILE HILANG | INFORMASI TIDAK AVAILABLE, UPLOAD ULANG DOKUMEN | 34000000000
GROWTH ? OR CHANGE
RISK REGISTER
| MODUL | ASSET | THREAT |  | RISK | IMPACT | ANALISIS |  |  | RPN | EVALUATION | THREATMENT | CONTROL CRITERIA | CONTROL TYPE | SOLUTION (GROWTH / CHANGE) | DETAIL
|  |  | ACTOR | EVENT |  |  | POSSIBILITY | SEVERITY/ EXPOSURE | DETECTION |  | EFFECT/ CONSEQUENCIES
| MOD PERKULIAHAN (MAHASISWA) | PEOPLE | DBA | MISSCONFIGURATION | DATA/ FILE HILANG | INFORMASI TIDAK AVAILABLE, UPLOAD ULANG DOKUMEN | 3 | 4 | 3 | 10 | 30000000000 | MITIGASI | CONTROL PREVENTIVE, CONTROL DETECTIVE, CONTROL DETTERENT | ADMINISTRATIVE , TECHNICAL ?, PHYSICAL ?
|  | PEOPLE | DBA | KELALAIAN | DATA/ FILE HILANG | INFORMASI TIDAK AVAILABLE, UPLOAD ULANG DOKUMEN | 1 | 5 | 3 | 9 | 34000000000 | ACCEPTANCE | CONTROL DETTERENT , CONTROL DETECTIVE , CONTROL CORRECTIVE | ADMINISTRATIVE , TECHNICAL ?, PHYSICAL ?
0
|  | JARINGAN | [7 empty] | 0
20 JUTA

## LOSS SCENARIO
Loss Scenario
RISK | THREAT | VULNERABILITY | IMPACT | LOSS SCENARION | RISK CRITERIA
KOMPONEN LAPTOP RUSAK KARENA TUMPAHAN AIR | AIR | BUKAN IP 67 (TIDAK ADA PELINDUNG) | DATA TIDAK AVAILABLE (KEGIATAN BELAJAR MENGAJAR) | 10000000 | HIGHT IMPACT
KOMPONEN LAPTOP RUSAK KARENA TUMPAHAN AIR | AIR | BUKAN IP 67 (TIDAK ADA PELINDUNG) | DATA TIDAK AVAILABLE (KEGIATAN TRANSAKSI VENDOR) | 100000 | LOW IMPACT

## EXAMPLE
A) | GOVERNANCE
| BU (SALES) | BU (MARKETING) | BU (PROCUREMENT) | BU (PRODUCTION)
SUBJECT AREA
DATA NASABAH
DATA GAJI
|  |  |  | CRITERIA |  | QUALITATIVE | SEMI-QUANTITATIVE | QUANTITATIVE | DESCRIPTION
B) | IDENTIFICATION |  |  | THREAT , VULNERABLE, RISK CRITERIA, CONSEQUANCY |  | HIGH | 3
| > ASSET IDENTIFICATION |  |  |  |  | MEDIUM | 2
| 1. SISTEM ABSENSI |  |  |  |  | LOW | 1
| 2. LAPTOP | [11 empty] | PROGRAM IS
| 3. SERVER |  |  | ASSET CRITERIA |  | SENSITIVE | 4
| 4. JARINGAN |  |  |  |  | CRITICAL | 3
| 5. USER |  |  |  |  | MEDIUM | 2
| 6. SKILL / KNOWLEDGE |  |  |  |  | LOW | 1
| 7. DEVELOPER |  |  | possibility , SEVERITY CRITERIA |  | HIGH | 3 | 80-100%
[6 empty] | MEDIUM | 2 | 50-79%
[6 empty] | LOW | 1 | <50%
|  |  |  | DETECTION |  | HIGH | 1
[6 empty] | MEDIUM | 2
[6 empty] | LOW | 3
C) | RISK PROFILE , THREAT ASSESMENT, VULNERABLE ASSES, ANALYSIS, RISK REGISTER, RISK TREATMENT , CONTROL |  |  |  |  | RISK | INHERENT RISK
RISK REGISTER
RISK PROFILE
| CONTEXT | ASSEST IDENTIFICATION | THREAT / VULNERABLE ASSESMENT
QUALITATIVE | SCOPE | ASSET | THREAT | ASSET( VULNERABILITY) | RISK = (THREAT X VULNERABLE X (CONSEQUENCY)) | UNCERTAINTY/ POSSIBILITY/ PROBABIITY/ LIKELIHOOD | IMPACT | SEVERITY | DETECTION | CONSEQUENCY (LOSS SCENARIO) | RPN ( LIKEHOOD X SEVERITY X DETECTION)
|  |  | RUSAK (MEDIUM) | TIDAK ADA PELINDUNG LATOP
LISTRIK TIDAK STABIL
| (BUSALES)- DATA NASABAH | LAPTOP (CRITICAL) | HILANG (HIGH) | PROSES PEMILIHAN LOKASI DIMANA LAPTOP AKAN DIGUNAKAN TIDAK KOMPREHENSIF TERKAIT PROSES PENUGASAN PEGAWAI (MEDIUM) | MEDIUM | LOW | SALES/ COLLECTION TIDAK DAPAT BEKERJA KARENA DATA ADA DI LAPTOP (HIGH) | HIGH | HIGH | LOW
SRANGAN VIRUS
PROSES (SISTEM ABSENSI) (MEDIUM)
PII (SENSITIVE)
SEMI QUALITATIVE | SCOPE | ASSET | THREAT | ASSET( VULNERABILITY) | RISK = (THREAT X VULNERABLE X (CONSEQUENCY)) | UNCERTAINTY/ POSSIBILITY/ PROBABIITY/ LIKELIHOOD | IMPACT | SEVERITY | DETECTION | QONSEQUENCY (LOSS SCENARIO) | RPN ( LIKEHOOD X SEVERITY X DETECTION)
|  |  | RUSAK (MEDIUM) | TIDAK ADA PELINDUNG LATOP
LISTRIK TIDAK STABIL
| (BUSALES)- DATA NASABAH | LAPTOP (CRITICAL) | 3 | 2 | 6 | 1 | SALES/ COLLECTION TIDAK DAPAT BEKERJA KARENA DATA ADA DI LAPTOP (HIGH) | 3 | 1 | 1 | 3
|  |  | SRANGAN VIRUS |  |  | 1 |  | 2 | 3 |  | 6
PROSES (SISTEM ABSENSI) (MEDIUM)
PII (SENSITIVE)
decision
QUANTITATIVE | SCOPE | ASSET | THREAT | ASSET( VULNERABILITY) | RISK = (THREAT X VULNERABLE X (CONSEQUENCY)) | UNCERTAINTY/ POSSIBILITY/ PROBABIITY/ LIKELIHOOD | IMPACT | RISK EXPOSURE/SEVERITY/ MAGNITUDE | DETECTION | CONSEQUENCY (LOSS SCENARIO) SLE = ASSET VALUE X EXPOSURE |  | RPN ( LIKEHOOD X SEVERITY X DETECTION) | RISK TREATMENT (ACCEPTANCE , AVOID, MITIGASI, TRANSFER) | PROJECT PAMERAN (BU SALES) PROJECT MANAGEMENT |  |  | DETERENT
|  |  | RUSAK (MEDIUM) | TIDAK ADA PELINDUNG LATOP | [9 empty] | LOGICAL | PHYSICAL | ADMINISTRATIVE | DETECTIVE
|  |  |  | LISTRIK TIDAK STABIL | [12 empty] | PREVENTIVE
| (BUSALES)- CRM | LAPTOP (CRITICAL) | 3 | 2 | 28800000 | 50% | SALES/ COLLECTION TIDAK DAPAT BEKERJA KARENA DATA ADA DI LAPTOP (HIGH) | 80% | 1 | 4800000 | 12000000 | 1920000 | DATA (ACCEPTANCE + MITIGASI ) LAPTOP (ACCEPTANCE, MITIGASI, TRANSFER) | CONTROL DETERENT, DETECTIVE, PREVENTIVE, CORECTIVE | CONTROL DETERENT, DETECTIVE, PREVENTIVE, CORECTIVE | CONTROL DETERENT | CORRECTIVE
|  |  | SRANGAN VIRUS |  |  | 1 |  | 2 | 3 |  |  | 0 |  |  |  |  | COMPENSATING (LAYER DEFEBNSE)
PROSES (SISTEM ABSENSI) (MEDIUM)
PII (SENSITIVE)
incident classification
[7 empty] | Terbakar sebagian | Laptop hilang tanpa data |  | 3 | acceptance | monitor
[7 empty] | terbakar 3/4 | Laptop hilang dengan data |  | 5
[7 empty] | terbakar seluruhnya | laptop hilang dengan data beserta PII |  | 23 jt + 2 jt + 10 M
Note on K53: Inhousetrainer.NET: SLE = ASSET VALUATION X EXPOSURE LAPTOP = 5 JT DATA SALES = 1 JT PII = 0
Note on N53: Inhousetrainer.NET: DETAIL ACCEPTABLE ()

## VALUASI
DATA | valuasi
10 | 10000000
SLE = ASSET VALUE X POSSIBILITY EXPOSURE
ALE = SLE X ARO
3000000 | 10000000 | 0.3
0.5
15000000
Note on C10: SLE
Note on D10: Asset Value
Note on E10: Possibility Exposure
Note on C11: ARO
Note on C12: ALE

## BCP DRP
| 10 | 4 | 4 | 2
RPO | RTO | SDO 1 | SDO 2 | SDO3
( MTD ) Max. Tolerable Downtime
| 20 |  |  |  |  | BCP
(M.A.D) Max. Allowable Downtime
| 20 |  |  |  |  | BCM
MTO - Maximum tolerable outage
| 24 |  |  |  |  | B.I.A
Risk Tolerance | Risk Apetite |  |  |  | Risk Capacity | Reputation
RPO | RECOVERY POINT OBJECTIVE (TOLERANSI KEHILANGAN DATA, PENENTUAN INTERVAL BACKUP)
RTO | RECOVERY TIME OBJECTIVE (MENGEMBALIKAN SISTEM DAN DATA)
SDO | SERVICE DELIVERY OBJECTIBE (SERVICE SIAP DIGUNAKAN)
MTD | MAX. TOLERABLE DOWNTIME (TOTAL MAX TOLERANSI WAKTU DARI RTO S.D SDO TIM IRT MENYELESAIKAN INSIDEN DISASTER RECOVERY)
MAD | MAX. ALLOWABLE DOWNTIME (TOTAL MAX KESELURUHAN PROSES DARI RTO S.D SDO YANG DIPERBOLEHKAN OLEH BISNIS )
MTO | MAX. TOLERABLE OUTAGE (max toleransi dari enterprise terhadap ketidak tersediaan layanan yang akan mempengaruhi reputasi organisasi - BIA)